COSC22001 - Final Project
Meeting 2 Minutes

Prepared from the agenda, attendance report, and meeting transcript

| Meeting | Final Project - Meeting 2 |
| --- | --- |
| Date | April 4, 2026 |
| Time | 8:54 PM - 9:31 PM |
| Purpose | Align on data-source aggregation, regional scope, EDA approach, and follow-up tasks. |

# Attendance

| Name | Role | First Join | Last Leave | Duration |
| --- | --- | --- | --- | --- |
| Kapil Patel | Presenter | 8:54 PM | 9:31 PM | 36m 55s |
| Josiah Baarbe | Organiser | 8:58 PM | 9:31 PM | 32m 33s |
| Ted Njoroge | Presenter | 9:03 PM | 9:31 PM | 27m 15s |

Attendance summary: 3 participants attended. Average attendance time: 32m 14s.

**Note: Ram was sick and unable to attend today’s meeting.

# Agenda Coverage

Reviewed roles and responsibilities for the project team.

Discussed how to aggregate data sources and agreed on a regional scope.

Discussed the preferred approach for exploratory data analysis (EDA).

Confirmed follow-up tasks and how the next meeting will be scheduled.

# Discussion Summary

## 1. Meeting with Professor Omar

The team agreed that Ted would email Professor Omar and suggest a Monday morning meeting during the usual class window (approximately 9:00 AM to 12:00 PM).

The purpose of that meeting is to review current progress, clarify project questions, and confirm whether the team may proceed with certain data-collection choices.

## 2. Roles and responsibilities

Kapil agreed to take on a facilitator role for meetings and continue with data collection/scraping.

Kapil also agreed to contribute on the model-training and model-selection side.

Ted confirmed he remains responsible for feature engineering.

Josiah indicated he would focus on visualization and on organizing work outputs in a clear format, such as notebooks and possible app-based visualizations.

## 3. Data sources and project scope

The team revisited whether the project should use municipal, regional, or province-wide data.

After discussion, the group agreed to focus on the Greater Toronto Area (GTA) as the working regional scope because it offers more data than a single municipality while remaining more targeted than province-wide data.

The group agreed it would be best to aggregate available data sources together and then remove duplicates during cleaning.

Kapil noted that an older dataset of about 30,000 listings was available, but the team concluded that datasets older than 12 months should not be included based on prior guidance from the professor.

Kapil reported that the current Zolo scraping process had produced roughly 15,000 usable listings after filtering out scraping noise and repeated/incorrect values.

## 4. Scraping and feature coverage

The team discussed whether the current scraper should be rebuilt to capture additional features from listing pages.

A key point raised was that keeping more features at the data-collection stage gives the group more flexibility later for cleaning, feature engineering, and model selection.

The team agreed to leave the current scraper running for now and revisit a more feature-rich rebuild after speaking with Professor Omar, especially to confirm whether scraping from Zolo is acceptable for the project and final report.

Kapil shared that listing pages may contain more useful variables, including walk score and related neighbourhood-accessibility information.

## 5. EDA approach and work organization

The team discussed using separate Jupyter notebooks to organize major project stages such as data collection/cleaning, EDA, feature engineering, and model training/model selection.

The group saw notebooks as a practical way to keep work clear, structured, and easy to review.

For EDA specifically, the group agreed there can be flexibility in the working process: Ryan/Ram may use Jupyter Notebook with Copilot or Power BI during analysis, but the final organized deliverables should be easy for the team to follow.

# Key Decisions

| Topic | Decision / Agreement |
| --- | --- |
| Regional scope | Use the Greater Toronto Area (GTA) as the project scope rather than only one municipality or the full province. |
| Data sources | Aggregate compatible recent data sources together, then remove duplicates during cleaning. |
| Dataset recency | Do not use data older than 12 months unless explicitly approved. |
| Scraper status | Keep the current scraper running for now; consider rebuilding it later to capture more features. |
| EDA format | Use a clear notebook-based structure for organizing the team’s work; allow flexibility in how EDA is performed. |
| Professor follow-up | Ask Professor Omar about meeting availability and whether Zolo scraping is acceptable for the project report. |

# Action Items

| Owner | Task | Priority | Status |
| --- | --- | --- | --- |
| Ted Njoroge | Email Professor Omar, copy the team, and request a meeting for Monday morning if possible; ask for an alternate time if unavailable. | High | Open |
| Kapil Patel | Continue current scraping workflow and review listing pages for additional features worth capturing in a future scraper rebuild. | High | In progress |
| Team | Prepare questions for Professor Omar about scraping ethics/permission and dataset use in the final report. | High | Open |
| Team | Aggregate recent data sources and plan for duplicate detection/removal during cleaning. | Medium | Open |
| EDA lead | Proceed with EDA using the preferred workflow, while keeping final outputs organized and reviewable. | Medium | Open |
| Team | Create a WhatsApp poll to schedule the next team meeting after hearing back from Professor Omar. | Medium | Open |

# Next Meeting

Status: To be scheduled after the team receives a response from Professor Omar. The group agreed to use a WhatsApp poll to confirm availability.